## PMP Questions
SNo. | Domain | Question | Option A | Option B | Option C | Option D | Correct Answer
1 | People | A team member is consistently late to the daily stand-up. What should the Scrum Master do? | Reprimand them in front of the team | Meet with them privately to discuss the impact on the team | Ignore it as long as their work is done | Ask the Product Owner to replace them | B
2 | People | Two senior stakeholders have conflicting requirements. What is the PM’s first step? | Choose the requirement from the more senior stakeholder | Escalate to the Sponsor | Facilitate a meeting between them to reach a consensus | Submit both to the Change Control Board (CCB) | C
3 | People | An agile team feels the Product Owner is micromanaging tasks. What should the Scrum Master do? | Tell the team to ignore the Product Owner | Coach the Product Owner on agile roles and servant leadership | Ask the team to follow all instructions | Take over the Product Owner's responsibilities | B
4 | People | A PM is leading a global virtual team. Team members feel disconnected. What should the PM do? | Require everyone to travel to headquarters | Set up periodic informal virtual "coffee breaks" to build rapport | Send more frequent status emails | Increase the number of mandatory project meetings | B
5 | People | A team member wants to learn a new skill not required now but useful later. What should the PM do? | Deny the request to save costs | Support the request as it builds team capability and motivation | Tell them to learn it on their own time | Replace them with someone who already has the skill | B
6 | People | During a meeting, a team member is constantly interrupted. What should the PM do? | End the meeting | Tell the members to speak louder | Intervene and ensure all voices are heard | Do nothing to avoid conflict | C
7 | People | A team is in the "Storming" phase. What is the PM's role? | Delegate all decisions | Provide high direction and support to resolve conflicts | Step back and let them fail | Dictate all tasks strictly | B
8 | People | The stakeholder is unhappy with progress. What should the PM do first? | Show them the project schedule | Meet with them to understand their concerns | Ignore the stakeholder | Ask the Sponsor to talk to them | B
9 | People | An agile team is distracted by "emergency" requests from a functional manager. What should the Scrum Master do? | Tell the team to work overtime | Meet with the functional manager to protect the team from interruptions | Add requests to the current sprint | Tell the team to ignore the manager | B
10 | People | A PM wants to empower the team. What is the best approach? | Assign every task personally | Define the "what" and let the team decide the "how" | Make all decisions in private | Ask for approval on every email | B
11 | People | A team member is underperforming due to a personal issue. What should the PM do? | Show empathy and discuss how to support them | File a formal HR complaint | Replace them immediately | Deduct their pay | A
12 | People | A PM is using Emotional Intelligence (EI) to manage conflict. What is the first step? | Self-awareness | Social skills | Empathy | Motivation | A
13 | People | A stakeholder wants to give orders directly to the team. What should the PM do? | Quit the project | Tell the team to listen to the stakeholder | Explain the communication protocol to the stakeholder | Charge the stakeholder for the extra work | C
14 | People | A PM holds a brainstorming session for complex problems. This is an example of: | Directing | Facilitating | Managing | Dictating | B
15 | People | A PM is mentoring a junior PM. What is the best way to help? | Give them all the data entry work | Provide feedback, guidance, and responsibility | Let them fail without help | Tell them to read the PMBOK Guide only | B
16 | People | A team member is recognized for excellent work. How should the PM reward them? | Give them more work | Use a reward system meaningful to the individual | Give everyone the same reward | Do nothing | B
17 | People | A virtual team member is not responding to emails. What should the PM do? | Assume they are lazy | Try a different communication medium (e.g., video call) | Report them to their manager | Remove them from the team | B
18 | People | A PM wants to ensure the team understands the vision. What should they use? | A 100-page report | A clear and concise project vision statement | A list of tasks | A budget spreadsheet | B
19 | People | Which conflict resolution technique leads to a "Win-Win"? | Collaborating/Problem Solving | Compromising | Forcing | Smoothing | A
20 | People | A PM uses "Servant Leadership." What is their primary focus? | Controlling the team | Supporting and enabling the team to succeed | Pleasing the Sponsor | Following the rules | B
21 | People | A team is diverse. What should the PM do? | Treat everyone exactly the same, ignoring culture | Promote cultural awareness and respect differences | Only hire people from one culture | Force everyone to adopt the PM's culture | B
22 | People | A team member does not follow "ground rules." What should the PM do? | Change the rules | Remind the member of the agreed-upon rules | Publicly shame them | Ignore it | B
23 | People | A PM wants to foster transparency in Agile. What is the best tool? | Private emails | A public Kanban board | Locked spreadsheets | Monthly status reports | B
24 | People | A stakeholder is worried about a specific risk. What should the PM do? | Involve the stakeholder in the risk analysis | Tell them not to worry | Hide the risk | Blame someone else | A
25 | People | A team member is "Over-allocated." What should the PM do? | Make them work 80 hours a week | Use resource leveling or prioritize tasks | Hire a new team | Tell them to work faster | B
26 | People | A PM is leading a team of experts. Which leadership style is best? | Autocratic | Participative/Laissez-faire | Micro-managing | Directing | B
27 | People | A project is being closed. What should the PM do for the team? | Celebrate successes and conduct "Lessons Learned" | Stop talking to them | Give them a bad review | Start the next project immediately | A
28 | People | A team is struggling with a technical hurdle. What should the PM do? | Solve it themselves | Bring in a subject matter expert (SME) to coach | Tell the team to figure it out | Cancel the project | B
29 | People | A manager takes a resource for an emergency. What should the PM do? | Negotiate with the manager for a replacement | File a lawsuit | Refuse to let the resource go | Stop the project | A
30 | People | A PM is building "Shared Understanding." What helps most? | Lengthy documents | Face-to-face communication and active listening | Strictly following the WBS | Only talking to the team leader | B
31 | People | An agile team is "Self-Organizing." This means: | They have no manager | They decide how to do their work as a team | They do whatever they want | They don't have to follow a budget | B
32 | People | A team member makes a mistake. What should the PM do? | Fire them | Use it as a learning opportunity | Blame them in the report | Hide the mistake | B
33 | People | A PM is identifying stakeholders. Who is a stakeholder? | Only the customer | Only the team | Anyone affected by the project | Only the PMO | C
34 | People | In RACI, the "A" stands for: | Assigned | Accountable | Authorized | Analyst | B
35 | People | A project is failing. The PM gathers the team to find out why. This is: | Blaming | Root Cause Analysis | Waste of time | Micromanagement | B
36 | People | A PM wants to improve team "Velocity." What should they focus on? | Working more hours | Removing impediments | Hiring more people | Cutting scope | B
37 | People | A team member feels their ideas are never heard. What should the PM do? | Tell them their ideas aren't good | Ensure they have a platform (e.g., Retrospective) | Ignore them | Promote them | B
38 | People | "Active Listening" involves: | Hearing but not responding | Confirming understanding and reflecting | Multi-tasking | Interrupting | B
39 | People | A team is "Co-located." This means: | They work in different cities | They work in the same physical space | They use the same software | They have the same manager | B
40 | People | What is a "T-Shaped" professional? | Someone who only knows one thing | Someone with deep expertise in one area and broad knowledge in others | Someone who works in a T-shaped building | A manager | B
41 | People | What is the best outcome of conflict? | Someone loses | Innovative solutions and better team cohesion | People quit | The project is delayed | B
42 | People | A "360-degree feedback" involves: | Only the PM's opinion | Feedback from peers, subordinates, and managers | A 360-minute meeting | Looking around the room | B
43 | People | A "Product Owner" is responsible for: | Managing the team's schedule | Maximizing product value and managing the backlog | Coding the product | Hiring the PM | B
44 | People | "Mentoring" is: | Telling someone what to do | A long-term professional relationship focused on growth | A one-time meeting | Formal training | B
45 | People | "Coaching" is: | Managing a sports team | Helping someone improve a specific skill | Telling them they are doing a bad job | Writing a report | B
46 | People | A "Burnup Chart" shows: | Total work completed vs. total scope | How much money is left | Team frustration | People who left | A
47 | People | A "Burndown Chart" shows: | Work added | Remaining work in a sprint | The budget | The schedule | B
48 | People | Negotiation should focus on: | Winning at all costs | Reaching an agreement that satisfies both parties | Trickery | Giving up | B
49 | People | What is a major risk in a "Virtual Team"? | Too much communication | Misunderstandings due to lack of non-verbal cues | No travel costs | People working too hard | B
50 | People | A "Project Charter" is important because it: | Lists every task | Formally authorizes the project | Contains the final budget | Is written by the team | B
51 | People | "Empowering" the team increases: | The PM's workload | Team ownership and motivation | The chance of failure | The budget | B
52 | People | A team member is an "Expert." The PM should: | Tell them exactly what to do | Involve them in decision-making | Ignore them | Feel threatened | B
53 | People | A stakeholder is "Resistant." The PM should: | Avoid them | Try to understand and address their concerns | Fire them | Force them | B
54 | People | A "Team Charter" includes: | Project budget | Team values and ground rules | Product specifications | Customer names | B
55 | People | "Psychological Safety" means: | The office is locked | Team members feel safe to take risks | Everyone is happy | No disagreements | B
56 | People | "Positive Feedback" should be: | Rare | Specific, timely, and sincere | General | Only for the PM | B
57 | People | A "Cross-functional" team has: | Only developers | Members from different departments | Only managers | No leader | B
58 | People | Motivation is influenced by: | Just money | Achievement and recognition | Working conditions only | Fear | B
59 | People | "McGregor’s Theory Y" assumes: | People hate work | People are self-motivated | People need constant watching | People are lazy | B
60 | People | "Maslow’s Hierarchy" ends with: | Food | Self-actualization | Safety | Social needs | B
61 | People | Using "Influence" over "Authority" is common in: | Military | Matrix organizations | Projectized organizations | Dictatorships | B
62 | People | When "Onboarding" a new member, a PM should: | Introduce them to the vision and their role | Give them work and leave | Tell them to figure it out | Ignore them | A
63 | People | Conflict in agile teams is often resolved: | By the PM | By the team during retrospectives | By the CEO | By coin flip | B
64 | People | A "Stakeholder Engagement Assessment Matrix" shows: | Current vs. desired engagement | Salaries | Phone numbers | Risks | A
65 | People | When "Negotiating" with a vendor, focus on: | Lying about budget | Interests, not positions | Being aggressive | First offer | B
66 | People | A "Sprint Retrospective" is for: | Showing the product | Improving process | Planning next sprint | Firing people | B
67 | People | A "Daily Stand-up" should last: | 15 minutes | 1 hour | 5 minutes | As long as needed | A
68 | People | The "Three Questions" of a Daily Stand-up focus on: | Cost and talk | Yesterday, today, and blockers | Time and budget | Philosophy | B
69 | People | A "Blocker" is: | A team member | Anything stopping the team | A finished task | A project goal | B
70 | People | "Servant Leaders" manage: | People | Environment and obstacles | Budget only | Schedule only | B
71 | People | Nodding during "Active Listening" shows: | Agreement | Listening and understanding | Tiredness | Desire to speak | B
72 | People | For a "Burned out" member, the PM should: | Give more work | Encourage time off and re-evaluate load | Tell them to be stronger | Ignore it | B
73 | People | A "Resource Management Plan" includes: | Names only | How resources are acquired and managed | Laptop prices | Schedule | B
74 | People | A "Power/Interest Grid" helps: | Calculate power | Determine stakeholder engagement strategy | Find critical path | Manage budget | B
75 | People | "Soft Skills" include: | Coding | Communication and leadership | Math | Scheduling | B
76 | People | The "Project Manager" is responsible for: | Doing all work | Project success and leadership | Making coffee | Approving Sponsor's vacation | B
77 | Process | "Defining a new project" is part of: | Initiating | Planning | Executing | Closing | A
78 | Process | The goal of a WBS is to: | List people | Decompose deliverables into manageable components | Create a schedule | Set budget | B
79 | Process | The "Critical Path" is: | Path with most tasks | Longest path with zero float | Shortest path | Most expensive path | B
80 | Process | "Analogous Estimating" is: | Math-based | Using actual costs from similar projects | Bottom-up | Random | B
81 | Process | "Parametric Estimating" uses: | Statistical relationships (e.g., $ per sq. ft.) | Expert judgment | WBS only | Team opinion | A
82 | Process | A CPI of 0.8 means: | Under budget | Over budget (only $0.80 value per $1 spent) | Ahead of schedule | 80% done | B
83 | Process | An SPI of 1.2 means: | Behind schedule | Ahead of schedule | Over budget | PM is young | B
84 | Process | "Earned Value" (EV) is: | Value of work actually performed | Money spent | Planned budget | Total budget | A
85 | Process | "Actual Cost" (AC) is: | Budget | Cost incurred for work performed | Money left | Profit | B
86 | Process | CV formula: | EV - AC | EV - PV | AC - EV | PV - EV | A
87 | Process | SV formula: | EV - AC | EV - PV | PV - EV | AC - PV | B
88 | Process | "Change Requests" are approved by: | PM only | CCB or defined authority | Team | Customer only | B
89 | Process | "Scope Creep" is: | Insects | Uncontrolled scope expansion | Good thing | Planned change | B
90 | Process | "Gold Plating" is: | Actual gold | Adding unrequested features | Following scope | Expensive resources | B
91 | Process | A "Risk Register" contains: | Big risks only | Identified risks, responses, and owners | Budget | Team names | B
92 | Process | "Risk Mitigation" involves: | Ignoring risk | Reducing probability or impact | Moving to third party | Avoiding | B
93 | Process | "Risk Transfer" involves: | Fixing | Shifting ownership (e.g., insurance) | Ignoring | Accepting | B
94 | Process | "Qualitative Risk Analysis" prioritizes by: | Dollars | Probability and impact | PM's mood | Schedule | B
95 | Process | "Quantitative Risk Analysis" involves: | Numerical simulation (e.g., Monte Carlo) | Categorizing | Listing | Talking | A
96 | Process | "Quality Assurance" focuses on: | Product | Process | Budget | Customer | B
97 | Process | "Quality Control" focuses on: | Deliverables | Process | PM | Vendor | A
98 | Process | "Pareto Chart" rule: | 80/20 | 50/50 | 100% | PM's rule | A
99 | Process | "Fishbone Diagram" use: | Tracking | Finding root cause | Scheduling | Risk ID | B
100 | Process | "Crashing" means: | Adding resources to shorten time | Parallel tasks | Deleting tasks | Faster work | B
101 | Process | "Fast Tracking" means: | Resources | Overlapping sequential tasks | Faster clock | Skipping checks | B
102 | Process | "Fixed Price" is best when: | Unknown scope | Well-defined scope | New PM | Agile | B
103 | Process | "Cost Plus" is best when: | Scope undefined | Fixed scope | No money | Short project | A
104 | Process | "T&M" is for: | Small/quick tasks or undefined scope | Bridges | Fixed scope | Large projects | A
105 | Process | "Procurement" is: | Hiring PM | Purchasing outside goods/services | Team management | Selling | B
106 | Process | A "Sprint" is: | Time-boxed iteration | Fast run | Meeting | Document | A
107 | Process | Backlog owner: | Scrum Master | Product Owner | Team | Sponsor | B
108 | Process | Sprint Backlog owner: | PO | Team | SM | PMO | B
109 | Process | User Story format: | As a [user], I want [action], so that [value] | Now | Task list | Deadline | A
110 | Process | DoD ensures: | Tiredness | Shared understanding of completion | Project end | Payment | B
111 | Process | "Velocity" is: | Work completed per sprint | Internet speed | Duration | PM speed | A
112 | Process | "Retrospective" timing: | Start | End of every sprint | Yearly | After firing | B
113 | Process | "Kanban" focuses on: | Visualizing and WIP limits | Sprints | Roles | Estimating | A
114 | Process | A "Spike" is for: | Bug fix | Research/Investigation | Feature build | Celebration | B
115 | Process | "Story Points" measure: | Relative effort/complexity | Hours | Days | Dollars | A
116 | Process | "Planning Poker" use: | Gambling | Estimating user stories | Choosing PM | Risks | B
117 | Process | "Hybrid": | Combines Waterfall and Agile | Electric cars | Software only | Two PMs | A
118 | Process | "Project Management Plan": | Single doc | Subsidiary plans and baselines | Schedule | WBS | B
119 | Process | "Integration": | Hiring | Coordinating all aspects | Coding | Talking | B
120 | Process | "Lessons Learned" update: | Only end | Throughout project | Never | On request | B
121 | Process | "Benchmarking": | Benches | Comparing to other projects | Testing | Budgeting | B
122 | Process | "Monte Carlo" for: | Gambling | Simulating risk outcomes | Scheduling | Quality | B
123 | Process | "Resource Leveling": | May delay project to balance load | Speed up | Lower cost | Increase scope | A
124 | Process | "Resource Smoothing": | Changes critical path | Uses available float, no delay | Balances | Budget affect | B
125 | Process | "Control Chart": | Process stability | Schedule | Budget | Performance | A
126 | Process | "JIT": | Reduces inventory cost | Increases | Delays | Software only | A
127 | Process | "Kaizen": | Stop | Continuous improvement | Fast | Quality | B
128 | Process | "Six Sigma": | Speed | Reducing defects | Cost | Scope | B
129 | Process | "TQM": | Quality team | Everyone | PM only | Customer | B
130 | Process | "COQ" includes: | Prevention, appraisal, failure | Price only | PM salary | Testing price | A
131 | Process | "Verified Deliverables": | Customer | Quality Control | Team | Sponsor | B
132 | Process | "Accepted Deliverables": | Customer (Validate Scope) | QC | PM | Dev | A
133 | Process | "Scope Statement": | Budget | Deliverables, assumptions, exclusions | Schedule | Team | B
134 | Process | "RTM" links: | People | Requirements to deliverables | Risk to Issue | Budget to Schedule | B
135 | Process | "Work Package": | Lowest WBS level | Box | Task | Phase | A
136 | Process | "Planning Package": | Gift | WBS component with known content but no activities | Task | Plan | B
137 | Process | "Rolling Wave": | End only | Near term detailed, future high level | No plan | Surfing | B
138 | Process | "PDM": | FS only | All relationships (FS, SS, FF, SF) | Circles | No logic | B
139 | Process | "Lead": | PM | Acceleration of successor | Metal | Delay | B
140 | Process | "Lag": | Fast | Mandatory delay | Error | Risk | B
141 | Process | "Bottom-up": | Fast | Accurate but slow | Inaccurate | Sponsor work | A
142 | Process | PERT Beta: | (O + 4M + P) / 6 | (O + M + P) / 3 | Sum | / 4 | B
143 | Process | "Management Reserve": | Known | Unknown-Unknowns | Known-Unknowns | Bonus | A
144 | Process | "Contingency": | Unknown | Known-Unknowns | Customer | Scope | B
145 | Process | "BAC": | Budget at Completion | Business | Control | Best | B
146 | Process | "EAC": | Estimate at Completion | Early | Controlled | Activity cost | A
147 | Process | "ETC": | Estimate to Complete | Time | Task | End | A
148 | Process | "TCPI": | To-Complete Performance Index | Total | Percent | Time | A
149 | Process | "Governance": | Laws | Framework guiding activities | PM rules | CEO orders | A
150 | Process | "Configuration": | Product specs and documentation | Hardware | Hiring | Budget | B
151 | Process | "Change Log": | All work | Change request status | Risks | Stakeholders | A
152 | Process | "Issue Log": | Risks | Current problems | Potential | Done tasks | B
153 | Process | "Communication Plan": | Who, what, when, how | Cost | Speaker | Phones | B
154 | Process | "Push": | Sending (e.g., email) | Finding | Meeting | Forcing | A
155 | Process | "Pull": | Email | Accessing (e.g., Intranet) | Call | Yelling | A
156 | Process | "Interactive": | Multidirectional | One-way | Report | Sign | B
157 | Process | "Risk Appetite": | Hunger | Willingness to take uncertainty | Avoiding | Taking all | A
158 | Process | "Threshold": | Unacceptable risk level | Start | End | Report | B
159 | Process | "Tornado": | Sensitivity Analysis | Schedule | Resource | Procurement | A
160 | Process | "Bidder Conferences": | Meet team | Common understanding for sellers | Lowest price | Customer happy | A
161 | Process | "Make-or-Buy": | Internal vs. External decision | Price | Vendor choice | Profit | B
162 | Process | "SOW": | Work for vendor | PM job | Roles | Vision | A
163 | Process | "Closing": | Acceptance, transition, archive | Stopping | Deleting | Firing | A
164 | Process | "Final Report": | Performance summary and benefits | All emails | Resume | Meeting list | A
165 | Process | "Knowledge Transfer": | End only | Throughout and at closing | Never | Agile only | A
166 | Process | Ultimate goal: | Docs | Value delivery | Schedule | Budget | B
167 | Business | PM must ensure compliance with: | Legal and organizational standards | PM rules only | Customer whims | No rules | A
168 | Business | "Business Value": | Tangible and intangible elements | Profit only | Price | Employees | A
169 | Business | "Business Case": | Benefits vs. Investment | PM preference | Team skill | Schedule | A
170 | Business | "Benefits Management Plan": | How benefits are measured/delivered | Team pay | Features | Risks | A
171 | Business | Project not aligned with strategy: | Keep working | Discuss with Sponsor to redirect/close | Change strategy | Hide it | B
172 | Business | "Organizational Culture": | Affects decisions/interactions | Weather | Nothing | Dress code | A
173 | Business | "PMO": | Supportive, Controlling, Directive | Bossy | Training only | A room | A
174 | Business | "NPV": | Positive for viability | Negative | Zero | Ignored | A
175 | Business | "IRR": | Higher is better | Lower | Irrelevant | Agile only | A
176 | Business | "Payback": | Time to recover investment | Team pay | End date | Risk | A
177 | Business | "Organizational Change": | Helping transition to the new state | Change PM | Change budget | Firing | A
178 | Business | "Compliance Audit": | Following regulations | PM working | Team happy | Pretty product | A
179 | Business | Change in government policy: | Ignore | Assess impact | Stop | Media | B
180 | Business | Ultimate goal: | Docs | Value delivery | Schedule | Budget | B